## Sheet1
[7 empty] | PRELIMINARY TIMELINE FOR THE MAYNARD SENIOR CENTER PROJECT | [29 empty] | **DRAFT**
[6 empty] | 2024 | [6 empty] | 2025 | [5 empty] | 2026 | [5 empty] | 2027 |  |  |  |  | 2028 | [5 empty] | 2029 | [5 empty] | 2030
|  |  | Jan-Mar |  | Apr-Jun |  | Jul-Sep |  | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep |  | Oct-Dec | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec
FY 2009-2012 CAPITAL PROJECTS
1 |  | Angier School
2 |  | LFCC Envelope
3 |  | Horace Mann Windows
4 |  | Elementary Schls Sprinklers (3)
5 |  | Angino Farm |  |  |  | Site Plan Review?
6 |  | Jackson Homestd Archives
7 |  | Police Lobby
8 |  | NSHS Fieldhouse
9 |  | School Masonry (5)
10 |  | School Roofs (6)
11 |  | Ed Center Generator
12 |  | School Accessibility (2)
13 |  | School Electrical Upgrades (5)
14 |  | School Boilers (2)
Angier School Project
Projects for Board Approval
1 |  | FA Day MS
2 |  | DPW - Replace Street Sweeper | [11 empty] | Design-Planning
3 |  | Energy Efficiency Ph I | [11 empty] | Construction - Purchase
4 |  | Burr School Mechanical
5 |  | Lincoln-Eliot Mechanical
6 |  | Fire Station #4 Windows
7 |  | LFCC Accessibility
8 |  | City Hall Veteran's Wing
9 |  | Fire Station #10
10 |  | Replace Comm Tower Bldg
11 |  | Bigelow Stairs
12 |  | Gath Pool Finishes
13 |  | Carr School Renovation
14 |  | School Water Infiltration
Countryside and Oak Hill
15 |  | Bowen Masonry
16 |  | Craft St Garage Envelope
17 |  | Fire Station 2 Boiler Replacement*
18 |  | Fire Dept. Replace Ladder Truck*
CDBG Funded Projects
19 |  | City Hall Accessible Lift
20 |  | Newton Centre Playground Access
21 |  | ADA Accessible Curb Cuts
[6 empty] | 2014 | [5 empty] | 2015 | [8 empty] | 2016
|  |  | Jan-Mar |  |  | Apr-Jun |  | Jul-Sep |  | Oct-Dec | Jan-Mar | Apr-Jun |  | Jul-Sep |  | Oct-Dec | Jan-Mar | Apr-Jun |  |  | Jul-Sep | [11 empty] | Oct-Dec | [5 empty] | Oct-Dec
* Additional Capital Investments beyond FY13 Approved CIP
ELEM. MODULAR CLASSRMS
TEMPORARY STATION #10 |  |  |  | Station 10 in Temp Station
STATION #10 and WIRES |  |  |  | 16 Months
3.5 Years Total
|  |  | Jan-Mar |  | Apr-Jun |  | Jul-Sep |  | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep |  | Oct-Dec | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec |  | Jan-Mar | Apr-Jun |  | Jul-Sep | Oct-Dec
|  |  | Project Phases | [10 empty] | Milestones
[6 empty] | Senior Center Focus Group | [8 empty] | Senior Center Focus Group and COA Organization and Advocacy
[6 empty] | Approvals | [8 empty] | Town Meeting Approval of Design Funds
[6 empty] | Feasibility / Schematic Design | [8 empty] | Request for Qualifications and Designer Selection Process
[6 empty] | Bid / Award | [8 empty] | Feasibility Site Search and Selection
[6 empty] | Design / Documents | [8 empty] | Feasibility / Schematic Design
[6 empty] | Construction | [8 empty] | Feasibility Study Approval - FinComm | [21 empty] | 2021-10-21
Feasibility Study Approval - Selectboard
Schematic Design / Site Plan Approval
Funding Approval - FinComm
Selectboard Project Approval
Town Meeting and Full Project Funding Approval
x
**DRAFT**
5
9
11
10
9
8
6
7
4
2
1
3
2
1
3
10
11