| Item | Action | Entity Responsible | Deadline |
| --- | --- | --- | --- |
| 1 | Project Eligibility Letter (PEL) Application submitted to Subsidizing Agency (in this case Mass Housing P’ship - MHP) | AvalonBay | N/A |
| 2 | Chief Elected Official (Chair of SB) receives official notification letter – comment period begins -- comments must be received within 30 days after receipt of official notification letter | MHP | 8/27/2024 |
| 3 | Extension of comment period requested (optional); if request approved then items 4 – 8 would be pushed out | Town | 8/27-9/4 |
| 4 | 1st SB meeting to introduce development and PEL application | AvalonBay, Town | 9/4/2024 |
| 5 | Site visit scheduled | MHP, Town | 9/16/2024 |
| 6 | 2nd SB meeting to receive public comment, give direction as to Town response | Town | 9/17/2024 |
| 7 | Comment period ends | MHP, Town | 9/26/2024 |
| 8 | PEL decision issued; A decision in the affirmative will unlock a new set of actions/deadlines of which the most important is ZBA rendering a determination on the Comprehensive Permit application within 180 days of receipt | MHP | Within approx. 2 weeks of 9/26/2024 |